THE FIRST 90 DAYS

Setting up and operating in the UAE

Setting up here is a chain, not a checklist. Premises gate registration, registration gates the licence, the licence gates the establishment card, and that gates every visa. Bank account opening runs alongside and is the slowest step of all. Sequence it wrong and the business is licensed but cannot pay anyone.

| Item | Detail |
| --- | --- |
| Business | [NAME] |
| Structure chosen | [Mainland LLC / free zone / DIFC / ADGM / branch] |
| Activities | [DESCRIBE] |
| Emirate or zone | [DETAIL] |
| Headcount — year one | [NUMBER] |
| Target trading date | [DATE] |
| Owner of the setup | [NAME] |
| Advisers | [Legal, tax, PRO] |

# THE FOUR DECISIONS THAT ARE HARD TO UNDO

| Decision | Why it is hard to reverse | Where to look |
| --- | --- | --- |
| Jurisdiction — mainland, free zone, DIFC or ADGM | Determines employment law, tax analysis, data regime and share mechanics | Choosing UAE jurisdiction; group structures |
| Where the equity sits | Mainland share transfers are notarised and slow; option schemes barely work there | Shareholders’ agreement; employee equity |
| Premises and space taken | Space determines visa quota and the lease runs for years | Setting up premises |
| Whether to register a commercial agency | Statutory protections attach and exit becomes very difficult | Commercial agency; distribution |

a	Redomiciliation between authorities is now possible, which makes the first decision less permanent than it was. It remains a process with approvals, not a switch.

THE 90 DAYS

| # | Step | When | Depends on | Owner | Done |
| --- | --- | --- | --- | --- | --- |
| Days 1–15 — decide |  |  |  |  |  |
| 1 | Jurisdiction chosen with legal and tax advice | Day 1–10 | — | [Founder] | [DATE] |
| 2 | Activities confirmed against the licence category | Day 5 | Step 1 | [Founder] | [DATE] |
| 3 | Ownership structure and where equity sits | Day 10 | Step 1 | [Founder] | [DATE] |
| 4 | Headcount modelled across the lease term | Day 10 | — | [Founder] | [DATE] |
| 5 | Name reserved | Day 12 | Step 2 | [PRO] | [DATE] |
| 6 | Initial approval obtained | Day 15 | Step 5 | [PRO] | [DATE] |
| Days 15–45 — establish |  |  |  |  |  |
| 7 | Attestation of foreign documents started | Day 1 — do not wait | — | [Founder] | [DATE] |
| 8 | Premises identified; quota checked against space | Day 20 | Step 4 | [Founder] | [DATE] |
| 9 | Lease signed | Day 25 | Step 8 | [Founder] | [DATE] |
| 10 | Tenancy registered (Ejari / Tawtheeq / zone) | Day 28 | Step 9 | [PRO] | [DATE] |
| 11 | [Mainland] MOA notarised | Day 30 | Steps 3, 6 | [PRO] | [DATE] |
| 12 | Trade licence issued | Day 35 | Steps 10, 11 | [PRO] | [DATE] |
| 13 | Bank account application submitted | Day 35 — immediately | Step 12 | [Founder] | [DATE] |
| 14 | Establishment card and immigration file | Day 40 | Step 12 | [PRO] | [DATE] |
| 15 | Visa quota confirmed | Day 42 | Steps 12, 14 | [PRO] | [DATE] |
| Days 45–75 — register and equip |  |  |  |  |  |
| 16 | Corporate tax registration | Day 45 | Step 12 | [Finance] | [DATE] |
| 17 | VAT registration assessed and made where required | Day 45 | Step 12 | [Finance] | [DATE] |
| 18 | UBO register established and filed | Day 45 | Step 12 | [CoSec] | [DATE] |
| 19 | Fit-out approvals — landlord, municipality, civil defence | Day 45–70 | Step 9 | [Admin] | [DATE] |
| 20 | Utilities and telecoms ordered | Day 45 — long lead times | Step 9 | [Admin] | [DATE] |
| 21 | Insurance arranged — health, work injury, liability | Day 50 | — | [Finance] | [DATE] |
| 22 | Accounting system and record-keeping established | Day 50 | — | [Finance] | [DATE] |
| 23 | Bank account opened | [Day 50–80] | Step 13 | [Founder] | [DATE] |
| Days 60–90 — hire and operate |  |  |  |  |  |
| 24 | Employment documents prepared for the jurisdiction | Day 60 | Step 1 | [HR] | [DATE] |
| 25 | Work permits applied for | Day 60 | Steps 14, 15 | [PRO] | [DATE] |
| 26 | Employees may not start before permits issue | Day 70+ | Step 25 | [HR] | [DATE] |
| 27 | MOHRE contracts registered within 14 days of permit approval | Day 75 | Step 25 | [HR] | [DATE] |
| 28 | WPS set up and tested before the first payroll | Day 80 | Steps 23, 27 | [Payroll] | [DATE] |
| 29 | Health insurance enrolled before visas | Day 75 | Step 21 | [HR] | [DATE] |
| 30 | Emiratisation position calculated | Day 85 | Step 27 | [HR] | [DATE] |
| 31 | Data protection policy and privacy notices adopted | Day 85 | Step 1 | [DPO] | [DATE] |
| 32 | Compliance calendar built with six-month reminders | Day 90 | All | [Founder] | [DATE] |

# WHAT DELAYS PEOPLE

| Cause | How long it adds | Prevention |
| --- | --- | --- |
| Attestation of foreign documents | 3–6 weeks | Start on day one, before anything else |
| Bank account opening | Weeks to months | Apply the day the licence issues; apply to several banks |
| Telecoms installation | [Weeks] | Order at lease signature |
| Fit-out approvals | [Weeks] | Design to what will be approved |
| Licence activity mismatch | [Weeks] | Confirm the activity before name reservation |
| Quota insufficient for the plan | Restructuring | Model headcount before signing the lease |
| Wrong jurisdiction chosen | Months | Take advice before incorporating |

# FIRST-YEAR OBLIGATIONS

| Obligation | Frequency | Missed most often |
| --- | --- | --- |
| WPS salary file | Monthly | Permit bans from the first offence |
| Emiratisation rate recalculated | Monthly | Target moves with every skilled hire |
| Free zone qualifying revenue analysis | Monthly | De minimis breach found too late |
| VAT returns where registered | [Quarterly] | Reverse charge on imported services |
| Corporate tax return | Annually | Filing required even with no tax due |
| UBO register updated | On change | Never updated after incorporation |
| Licence, card and tenancy renewals | Annually | Started too late; the cascade |
| Records retained seven years | Continuous | Working papers discarded |

# WHERE TO LOOK IN THIS LIBRARY

| If you are… | Start with |
| --- | --- |
| Deciding where to establish | Choosing UAE jurisdiction; free zone formation; mainland LLC incorporation |
| Hiring your first employee | Employee onboarding; employment contract; offer of employment |
| Setting up payroll | Running payroll; WPS compliance; end-of-service gratuity |
| Taking premises | Setting up premises; commercial tenancy; fit-out and construction |
| Registering for tax | Corporate tax and QFZP; corporate tax return; VAT and e-invoicing |
| Raising investment | Raising investment; shareholders’ agreement; convertible instruments |
| Appointing a distributor | Commercial agency and distribution — read before agreeing anything |
| Handling personal data | PDPL policy; DIFC or ADGM policy; data processing addendum |
| Building a group | Group structures; transfer pricing; secondment |
| Letting someone go | Offboarding; settlement agreement; redundancy and restructuring |
| Staying compliant | Annual compliance calendar — the cascade in one place |

NOTES FOR USE

Delete this page before execution. It is guidance, not part of the agreement.

Setting up is a chain, not a checklist

Premises gate registration, registration gates the licence, the licence gates the establishment card, and that gates every visa transaction. Working the steps out of order produces a business that is licensed but cannot hire or pay anyone.

Start attestation on day one

Foreign incorporation documents, powers of attorney, degree certificates and marriage certificates all need attestation in the country of origin, embassy legalisation and Ministry of Foreign Affairs attestation. Three to six weeks, and almost everything else waits on it.

Apply for the bank account the day the licence issues

It is the slowest step and it sits on the critical path to payroll. Apply to several banks in parallel, prepare the source of wealth narrative in advance, and expect substantial diligence on the ownership chain.

Model headcount before signing the lease

Visa quota is linked to the area and type of premises, and the lease runs for years. A company that minimises space to control cost and then wins work finds it cannot hire. This is the most common structural mistake in year one.

Take advice on jurisdiction before incorporating

Mainland, free zone, DIFC and ADGM differ on employment law, tax, data protection and share mechanics. Redomiciliation is now possible, which softens the consequence, but it is a process with approvals rather than a correction.

Decide where the equity sits before the first investor

A mainland LLC makes share transfers, option schemes and founder vesting genuinely difficult. Groups raising investment normally place the equity at an ADGM, DIFC or offshore holdco. Retrofitting that after a round has closed is materially harder.

Register for corporate tax even with no tax due

Registration is mandatory regardless of expected liability, including for free zone entities and businesses claiming reliefs. It is the most common first-year compliance failure and it is entirely avoidable.

Employees cannot start before the permit issues

Business pressure to have someone begin informally during processing is common and unlawful. Set the start date from the permit, not the offer, and register the MOHRE contract within 14 days of permit approval.

Test WPS before the first payroll

No bank account means no WPS, and WPS breaches carry permit consequences from the first offence. Set it up and run a test before the first pay date rather than discovering a problem on the day.

Build the compliance calendar in the first 90 days

Licence, card, tenancy, permits and visas all renew, and each gates the next. Six-month reminders built while the dates are in front of you prevent the cascade that stops businesses in year two.

Recalculate Emiratisation with every skilled hire

On the mainland the target moves with the skilled workforce, so a company hiring through year one can fall out of compliance without losing anyone. Make the recalculation part of hiring approval.

Free zone entities must track intra-group revenue

Selling to a mainland affiliate is non-qualifying revenue counting against a de minimis of the lower of AED 5,000,000 or 5% of total. Found at year end it cannot be prevented; found monthly, one engagement can be restructured.

Do not register a commercial agency without advice

Registration gives the counterparty statutory exclusivity, constrained termination and compensation rights that no contract can displace. It is among the few decisions here that can be effectively irreversible.

Keep records from day one

Seven years for tax, permanently for corporate records. Companies reconstruct their constitutional history painfully at their first financing or sale, and gaps in the chain are genuinely difficult to remedy later.

Current as of

Reflects UAE requirements current as of [DATE OF USE]. Licensing procedures, ownership rules, tax registration deadlines, permit and quota requirements, Emiratisation targets and free zone rules all differ by emirate and zone and change — take UAE legal and tax advice before establishing, and confirm each step with the relevant authority.